## FrontCover
AFRICA CENTRE of EXCELLENCE (ACE) PROJECT
KNUST ENGINEERING EDUCATION PROJECT (KEEP)
KWAME NKRUMAH UNIVERSITY OF SCIENCE AND TECHNOLOGY
(KNUST) KUMASI, GHANA
2019/2020 ACADEMIC YEAR
PROCUREMENT PLAN FOR GOODS/WORKS/TECH. SERVICES

## ACE Plan Goods 2020
Kwame Nkrumah University of Science and Technology
Budget Period:- January 2020- December 2020- GOODS
| Sources of Funding:- World Bank |  |  | BASIC DATA |  |  |  | Tendering Period |  |  | Tender Evaluation |  | Contract Finalization |  |  | Goods Delivery
| Contract Package* | Plan VRS Actual | Package Number | Estimated Amount (USD$) | Procurement Method | Final Authority for Contract Award | Tender Document Preparation & Submission by Ex Agency | Tender Invitation Date | Tender Closing Date | Submission of Tender Eval. Report | Approval by Final Authority | Contract Amount (USD$) | Date Contract Award | Date Contract Signature | Arrival of Goods | Inspection Final Acceptance
0001 | Procurement of teaching equipment, laptops, E-learning facilities,etc | PLAN | ACE/KNUST/GD/0001/2019/20 | 80000 | NCB | CTRB | 2020-06-15 | 2020-06-20 | 2020-07-20 | 2020-08-03 | 2020-12-31 | 80000 | N/A | N/A | N/A | N/A
ACTUAL
0002 | Procurement of laboratory equipment and consumables | PLAN | ACE/KNUST/GD/0002/2020/21 | 79000 | NCB | CTRB | 2020-06-15 | 2020-06-20 | 2020-07-20 | 2020-08-03 | 2020-12-31 | 79000 | N/A | N/A | N/A | N/A
ACTUAL
0003 | Procurement of 1 No. 4x4 cross country vehicle | PLAN | ACE/KNUST/GD/0003/2020/21 | 125000 | NCB | CTRB | 2020-06-15 | 2020-06-20 | 2020-07-20 | 2020-08-03 | 2020-12-31 | 125000 | N/A | N/A | N/A | N/A
ACTUAL
0004 | Procurement of office equipment and office furniture and fittings | PLAN | ACE/KNUST/GD/0004/2020/21 | 20000 | NCB | CTRB | 2020-06-15 | 2020-06-20 | 2020-07-20 | 2020-08-03 | 2020-12-31 | 20000 | N/A | N/A | N/A | N/A
ACTUAL
| TOTAL |  |  | 304000 | [7 empty] | 304000
Acronyms:
NCB:- National Competitive Bidding
ICB:- International Competitive Bidding
RT:- Restricted Tendering
SS:- Single Source
MTRB:- Ministerial Tender Review Board
CTRB:- Central Tender Review Board
PPA | Public Procurement Authority
Formulas:
Tender Closing Date = [Tendering Period]+30
Submission of Tender Eval. Report = [Tender Closing Date]+14
Tender Evaluation = [Submission of Tender Eval. Report]+150

## ACE Plan Works 2020
Procurement Entity:- Kwame Nkrumah University of Science and Technology
Budget Period : January 2020 - December 2020
| Sources of Funding:- World Bank | Plan | Package Number | Estimated Amount | Procurement Method | Authority for | Tendering Periods |  |  | Tender Evaluation |  | Contract Finalization |  |  | Contract Implementation
NO | Contract Package | Vrs |  | USD$ |  | Procurement | Prep. & Submission | Tender Invitation | Tender | Submission | Approval by | Contract Amount | Contract Award | Contract Signature | Mobilization/ | Substantial Completion | Final | Final
|  | ACTUAL |  |  |  | Decision | by Ex Agency | Date | Closing-Opening | Tender Evaluation Report | Final Authority | USD$ | Date | Date | Advance Payment | As Specified | Aceptance | Cost (USD$)
0001 | Construction of Postgraduate classrooms, research building and offices and fixing of air conditioners | PLAN | ACE/KNUST/WKS/0001/2019/23 | 1174118 | Pre-Qualif. | CTRRB | 2020-04-30 | 2020-05-30 | 2020-09-27 | 2020-10-17 | 2020-12-16 | 1174118 | 2020-12-23 | N/A | N/A | N/A | N/A | 1174118
ACTUAL
| TOTAL |  |  | 1174118 | [7 empty] | 1174118 | [5 empty] | 1174118
Formulas:
Tender Invitation = [Tendering Periods]+30
Tender = [Tender Invitation]+120
Tender Evaluation = [Tender]+20
Approval by = [Tender Evaluation]+60
Contract Award = [Approval by]+7

## ACE Consultancy Serv. 2020
Procurement Entity:- Kwame Nkrumah University of Science and Technology
Budget Period:- January 2020 - December 2020- SERVICES
| Sources of Funding:- World Bank | PLAN | Package Number | Estimated Amount | Selection | Authority for | Consultants Proposals |  |  | Proposal Evaluation Technical(T) & Financial (F) |  |  |  | Negotiation |  |  | Contract Finalization |  |  | Contracrt Implementation
| Contract Package | Vrs |  | USD$ | Selection Method | Contract Award | Preparation of Request for | Tender Invitation | Submission Date | Complete | Opening | Complete | Approval of Evaluation | Complete | Approval of | Submission of Draft | Contract Amount | Contract | Contract |  | Draft Report | Final Report | Final
|  | ACTUAL |  |  |  | Decision | Proposals | Date | Financial + Technical Proposals | Technical Evaluation | Financial Proposals | Evaluation Report (T)(F) | Report (T)(F) | Negotiation | Negotiation Report | Contract | USD$ | Award Date | Signature | Advance Payment | Date | Date | Cost (USD$)
001 | Recruitment of an individual consultant to facilitate and develop GAP assessment of post graduate education in COE | PLAN | ACE/KNUST/SERV/001/2019/23 | 20000 | Price Quotation | Contract Award | 2020-04-05 | 2020-07-14 | 2020-10-22 | 2020-11-01 | 2020-11-11 | 2020-11-26 | 2020-11-25 | 2020-11-27 | 2020-12-02 | 2020-12-10 | 20000 | 2020-12-17 | 2020-12-20 | N/A | N/A | N/A | 20000
ACTUAL
002 | Recruitment of individual consultant to design and develop laboratory training Curriculum for staff | PLAN | ACE/KNUST/SERV/002/2019/23 | 50000 | NCB | Contract Award | 2020-04-05 | 2020-07-14 | 2020-10-22 | 2020-11-01 | 2020-11-11 | 2020-11-26 | 2020-11-25 | 2020-11-27 | 2020-12-02 | 2020-12-10 | 50000 | 2020-12-17 | 2020-12-20 | N/A | N/A | N/A | 50000
ACTUAL
| TOTAL |  |  | 70000 | [12 empty] | 70000 | [5 empty] | 70000
Formulas:
Tender Invitation = [Consultants Proposals]+100
Submission Date = [Tender Invitation]+100
Complete = [Submission Date]+10
Complete = [Opening]+15
Opening = [Complete]+10
Approval of Evaluation = [Opening]+14
Negotiation = [Approval of Evaluation]+2
Approval of = [Negotiation]+5
Submission of Draft = [Approval of]+8
Contract = [Submission of Draft]+7
Contract = [Contract]+3

## APPENDIX.
APPENDIX A:
OTHER PROCURING ENTITIES - THRESHOLDS FOR REVIEW/APPROVAL AUTHORITY (AMOUNTS IN US&)
Authority | Goods | Works | Technical Services | Consulting Services
(1) Vice-Chancellor | Up to $25,000.00 | Up to $37,500.00 | Up to $25,000.00 | Up to $25,000.00
(2) KNUST Tender | >$25,001.00 -$,200,000.00 | >$37,500.00 - $250,000.00 | >$25,001.00 -$,200,000.00 | >$25,001.00 -$,200,000.00
(4) Central Tender Review Board (CTRB) | Above $200,000.00 | Above $250,000.00 | Above $200,000.00 | Above $200,000.00

## ACE Plan Tech. Services 2016 (hidden)
Procurement Entity:- Kwame Nkrumah University of Science and Technology
Budget Period:- January 2016 - December 2016
| Sources of Funding:- World Bank |  |  | BASIC DATA |  |  | Tendering Period |  |  | Tender Evaluation |  | Contract Finalization |  |  | Service Delivery
| Contract Package* | Plan VRS Actual | Package Number | Estimated Amount (GH¢) | Procurement Method | Final Authority for Contract Award | Tender Document Preparation & Submission by Ex Agency | Tender Invitation Date | Tender Closing Date | Submission of Tender Eval. Report | Approval by Final Authority | Contract Amount (Cedis) | Date Contract Award | Date Contract Signature | Delivery of Service | Inspection Final Acceptance
1 | Recruitment of an individual Architectural, structural, quantity surveying and services consultants | PLAN | ACE/KNUST/TSERV/2016/1 | 36000 | NCB | MTRB | 2016-01-06 | 2016-01-14 | 2016-02-13 | 2016-02-20 | 2016-02-25 | 36000 | 2016-03-01 | 2016-03-03 | 2016-03-23 | 2016-03-30
ACTUAL
2 | Recruitment of an individual consultant to review and design curriculum for new course content | PLAN | ACE/KNUST/TSERV/2016/2 | 50000 | NCB | MTRB | 2016-01-06 | 2016-01-21 | 2016-02-20 | 2016-03-19 | 2016-04-02 | 50000 | 2016-04-16 | 2016-04-30 | 2016-07-29 | 2016-08-05
ACTUAL
3 | Recruitment of an individual consultant to review staff capacity and train faculty in specialized skills | PLAN | ACE/KNUST/TSERV/2016/3 | 50000 | NCB | MTRB | 2016-01-06 | 2016-01-21 | 2016-02-20 | 2016-03-19 | 2016-04-02 | 50000 | 2016-04-16 | 2016-04-30 | 2016-07-29 | 2016-08-05
ACTUAL
4 | Recruitment of an international accreditation specialist as individual consultant to support International accreditation application | PLAN | ACE/KNUST/TSERV/2016/4 | 50000 | NCB | MTRB | 2016-01-06 | 2016-01-21 | 2016-02-20 | 2016-03-19 | 2016-04-02 | 50000 | 2016-04-16 | 2016-04-30 | 2016-07-29 | 2016-08-05
ACTUAL
5 | Recruitment of individual consultant to review and design laboratory training Curriculum for staff | PLAN | ACE/KNUST/TSERV/2016/5 | 50000 | NCB | MTRB | 2016-01-06 | 2016-01-21 | 2016-02-20 | 2016-03-19 | 2016-04-02 | 50000 | 2016-04-16 | 2016-04-30 | 2016-07-29 | 2016-08-05
ACTUAL
6 | Recruitment of one Project Administration and Accounting Assistant | PLAN | ACE/KNUST/TSERV/2016/6 | 70000 | ICB | MTRB | 2016-01-06 | 2016-01-21 | 2016-02-20 | 2016-03-19 | 2016-04-02 | 70000 | 2016-04-16 | 2016-04-30 | 2016-07-29 | 2016-08-05
ACTUAL
7 | Recruitment of one Post Doc. for academic and research management assistance | PLAN | ACE/KNUST/TSERV/2016/7 | 110000 | ICB | CTRRB | 2016-01-06 | 2016-01-21 | 2016-02-20 | 2016-03-19 | 2016-04-02 | 110000 | 2016-04-16 | 2016-04-30 | 2016-07-29 | 2016-08-05
ACTUAL
8 | Recruitment of an individual consultant to support the design and build a website | PLAN | ACE/KNUST/TSERV/2016/8 | 20000 | NCB | MTRB | 2016-01-06 | 2016-01-21 | 2016-02-20 | 2016-03-19 | 2016-04-02 | 20000 | 2016-04-16 | 2016-04-30 | 2016-07-29 | 2016-08-05
ACTUAL
| TOTAL | TOTAL |  | 436000 | [7 empty] | 436000
Formulas:
Tender Invitation Date = [Tendering Period]+8
Tender Closing Date = [Tender Invitation Date]+30
Tender Evaluation = [Tender Closing Date]+7
Approval by Final Authority = [Tender Evaluation]+5
Date Contract Award = [Approval by Final Authority]+5
Date Contract Signature = [Date Contract Award]+2
Service Delivery = [Date Contract Signature]+20
Inspection Final Acceptance = [Service Delivery]+7