## Sheet1
Name of Center | KNUST ENGINEERING EDUCATION PROJECT
Institution | Kwame Nkrumah University of Science and Technology |  |  | On Schedule
Country | GHANA
Center Leader | Professor Kwabena Biritwum Nyarko |  |  | Behind Schedule
Annual Workplan (Month XXX-Month XXX, Year) | JANUARY 2023-DECEMBER 2023
Work Plan Activities | Description | Partner Contribution (if relevant) | 2023 Y2Q1 |  |  | 2023 Y2Q2 |  |  | 2023 Y2Q3 |  |  | 2023 Y2Q4 |  |  | Milestone/Output | If NEW, Provide Justification | Estimated Budget($) | Estimated Revenue ($) | Contribution from Partner ($) | Person Responsible
|  |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Action 1: Centre Governance
Sub-Action 1a: Industrial Advisory Board
Activity 1: Quarterly meetings | Meeting to brief members on current status of project and receive suggestions and opinions to ensure project is relevant to needs of industry | [13 empty] | IAB meeting held every quarter with minutes attached |  | 2000 |  |  | Project Lead, Project Manager
Sub-Action 1b:International Scientific Advisory Board
Activity 1: Quarterly meetings | Meeting members to brief them of progress especially in the research thematic areas and seeking for views to enhance the quality of research | [13 empty] | ISAB meeting held every quarter with minutes attached |  | 1000 |  |  | Project Lead, Project Manager
Action 2: DLI 3:Quantity of Students
Sub-Action 2a: Media Advertisement
Activity 1: Advert of admissions on electronic and print media | Putting the call for admissions on the websites and dailies | [13 empty] | To ensure that all eligible students have access to the information to apply |  | 2000 |  |  | Marketing/Outreach Officer, Project Manager
Sub-Action 2b: Recruitment of students (15 PhDs and 20 MSc's)
Activity 1: Admission of students by departments | Postgraduate students admitted into the various departments | [13 empty] | Postgraduate students admitted by departments |  |  |  |  | Heads of Departments
Activity 2: Students shortlisted for scholarships | Postgraduate students meeting scholarship policy criteria shortlisted | [13 empty] | Scholarship list compiled |  |  |  |  | Heads of Departments, Deputy Project Lead, Project Manager
Activity 3: Scholarship interviews held | Panel constituted to conduct interviews | [13 empty] | Scholarship interview held with eligible list compiled |  | 4000 |  |  | Research Thematic Leads, Deans, Heads of Departments
Activity 4: Payment of tuition fees, accommodation and stipends | Postgraduate students tuition fees paid to the college | [13 empty] | Postgraduate students tuition fees paid to the college |  | 549000 |  |  | Project Accountant
Sub-Action 3a: Accreditation
Activity 1: Conducting an International Accreditation | Accreditation of 7 engineering programmes internationally to ensure they meet world class standards | [13 empty] | Cluster of programmes internationally accredited by AQAS and submitted to AAU for verification |  | 50000 | 400000 |  | AQAS
Sub-Action 3b: Design of New Courses
Activity 1: Curriculum for new course under the Energy Theme developed subject to recommendation from Gap Assessment | Curriculum for new course under the Energy Theme developed subject to recommendation from Gap Assessment | [13 empty] | New course under the Energy Theme presented to the College Boatd for approval |  | 2000 |  |  | Head of Mechanical Engineering
Activity 2: Curriculum for new course under the Digital Theme developed subject to recommendation from Gap Assessment | Curriculum for new course under the Digital Theme developed subject to recommendation from Gap Assessment | [13 empty] | New programme in PHD, MPhil & MSc in Machine Learning introduced |  | 2000 |  |  | Head of Computer Engineering
Sub-Action 3c: Postgraduate building and Procurement
Activity 1: Postgraduate building | Postgraduate building completed and fully operational by faculty and students | [13 empty] | Third milestone verified |  | 25000 | 300000 |  | World Bank Expert, Contractor
Activity 2: Realigning the postgraduate building into a smart one | Postgraduate classrooms, offices and labs will have a smart and conducive atmosphere for learning | [13 empty] | Partitioning, installation of state of the art equipment such as automated doors, teleconference equipment will have been done |  | 300000 |  |  | Contractors
Activity 3 : Purchase of additional equipment for the thematic Labs | Equipping the thematic labs with equipment to meet new engineering trends | [13 empty] | Additional equipment purchased |  | 100000 |  |  | Contractors
Activity 4: Setting up of a Quantum Lab | Set up of a quantum lab to build capacity of students in computing | [13 empty] | Set up of quantum lab with requisite equipment |  | 30000 |  |  | Thematic Lead, Digital Development Technologies
Action 4: DLI 5:Relevance of Education
Sub-Action 4a: Internships
Activity 1: 100 Internships for students and faculty members | Internships to bridge the relationship between academia and industry and to make academa more responsive to the needs of industry | [13 empty] | 100 Faculty members and students internships completed with list submitted to AAU for verification |  | 35000 | 100000 |  | Partnership Coordinator, Project Manager
Sub-Action 4b: Regional Conference and Capacity Building
Activity 1: Regional Conference held | Regional conference for students and faculty members to present, network and hold discussions on similar thematic areas | [13 empty] | An Engineering, Science, Technology and Entrepreneurship (ESTE) conference on Technology and Innovation for a Post Covid Recovery and Growth held |  | 40000 |  |  | ESTE Conference committee members
Activity 2: Staff and Faculty Training | Staff and Faculty members to participate in relevant workshops and conferences in relation to postgraduate engineering education and project management | [13 empty] | Staff and Faculty members travelling to participate in workshops and conferences both in and outside Ghana |  | 40000 |  |  | Project Manager, Project Accountant
Activity 4: Summer School | Summer school held for the Colleges of Engineering in the sub-region to enhance peer learning | [13 empty] | Summer school held |  | 40000 |  |  | Postgraduate Coordinators, Research Thematic Leads, Partnership Coordinator
Sub-Action 4c: College of Engineering Innovation Fund and Seminar Series
Activity 1: Promoting entrepreneurship, innovations through CoE Innovation Fund | Call for proposals rolled out (second cohort) | [13 empty] | Support granted to successful students |  | 50000 |  |  | Quality Assurance and Innovations Coordinator
Activity 2: Commercialisation and Registration of innovations | Innovations under cohort 1 fully commercialised and registered | [13 empty] | Registration of start-ups which are fully operational. Set-ups will be mentored by industry players |  | 15000 |  |  | Quality Assurance and Innovations Coordinator
Activity 3: Seminars delivered by industry players | Seminars under the various thematic areas held | [13 empty] | Academia-Industry linkage enhanced |  | 10000 |  |  | Research Thematic Leads, Project Manager
Activity 4: Partitioning of College of Engineering Innovation Centre | Partitioning of classrooms on the 2nd floor of the Bamfo Kwakye Building to create a larger space for members of the centre | [13 empty] | Partitioning of building completed with office |  | 50000 |  |  | Contractors
Activity 5: Purchase of furniture and equipment for Innovation Centre | Making the environment conducive for learning and creativity through the provision of requisite logistics | [13 empty] | Purchase of equipment and furnishing completed |  | 50000 |  |  | Contractors
Activity 6: Recruitment of an Innovations Manager | Interview of eligible candidates for Innovations Manager | [13 empty] | Innovations Manager recruited and commenced work |  | 10000 |  |  | Project Manager, College Registrar
Action 5: DLI 6: Timeliness and Quality of Fiduciary Management
Sub-Action 5a: Timely Fiduciary Reporting
Activity 1: Financial and Procurement Audit prepared | Audit to ensure that we are adhering to the world class standards of financial management practices | [13 empty] | Audit for the year 2022 completed and uploaded to KEEP website |  | 10000 | 22000 |  | Project Accountant
Activity 2: IFR for the period ending June 30th and Dec, 31st prepared | KEEP to ensure that IFR is prepared, reviewed and uploaded to website | [13 empty] | IFR will be prepared, reviewed and uploaded to website on 14th Aug for June report and 31st Dec for the December, 2022 report |  |  |  |  | Project Accountant
Sub-Action 5b: Web Transaprency of ACE Expenditures
Activity 1: Annual work plan for 2023 will be prepared and approved, budget, IFR and Procurement Audit reports completed | Annual work plan for 2023 will be prepared and approved, budget, IFR and Procurement Audit reports uploaded to website | [13 empty] | Annual work plan for 2022will be prepared and approved, budget, IFR and Procurement Audit reports uploaded to website |  |  | 22000 |  | Project Accountant
Action 5: Communication
Activity 1: Production of quarterly newsletters | Communication Officer, Content and Production Editors agree on the content for the newsletter | [13 empty] | Newsletter circulated to all stakeholders |  | 3000 |  |  | Communications Officer
Activity 2: Design and print KEEP brochures, pull ups, flyers and souvenirs | Design and print KEEP brochures, pull ups, flyers and souvenirs (calendars, pens, t shrts) | [13 empty] | Visibility of KEEP enhanced |  | 3000 |  |  | Communications Officer
Activity 3: Working on documentaries, jingles, short videos and advertising KEEP on traditional social media | Documentaries, Jingles and short videos in wide circulation on social media platforms | [13 empty] | Enhancing of visibility on social media platforms |  | 5000 |  |  | Communications Officer
Activity 4: Working on KEEP Impact Report | Relaying to stakeholers the impact made by KEEP in relation to the Disbursement Link Indicators (DLI's) | [13 empty] | Distributing the Impact Report to stakeholders |  | 2000 |  |  | Communications Officer
Activity 5: Interview of Thematic Leads and Faculty members on cross-cutting research taking place | Interview of Thematic Leads and Faculty members on cross-cutting research taking place | [13 empty] | Impact reports printed in hard prints and also located on social media platforms |  | 2500 |  |  | Communications Officer
Action 6: Alumni Relations
Activity 1 : Registration of Alumni | Capturing database of alumni who have completed the College of Engineering | [13 empty] | Registration of Alumni ongoing |  |  |  |  | Alumni Relations Officer
Activity 2: Alumni Chapter Meetings | Holding meetings with Alumni in the various regions | [13 empty] | Chapter meetings held |  | 20000 |  |  | Alumni Relations Officer
[17 empty] | 1449500 | 844000
Note on U6: Schenineda: If the addition of an activity or component requires further clarification, state it. Expecially since COVID may alter center activities and focus