## Cover Page
AFRICA CENTRE of EXCELLENCE (ACE) PROJECT
KNUST ENGINEERING EDUCATION PROJECT (KEEP)
KWAME NKRUMAH UNIVERSITY OF SCIENCE AND TECHNOLOGY
(KNUST) KUMASI, GHANA
2022/2023 ACADEMIC YEAR
PROCUREMENT PLAN FOR GOODS/WORKS/TECH. SERVICES-UPDATED

## Goods
Procurement Entity: -Kwame Nkrumah University of Science and Technology
Budget Period:- January 2023 - December 2023- GOODS
|  | BASIC DATA | [5 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  |  | Contract Implementation
Description* | Package Number | Lot Number | Estimated Amount in US $ | Procurement Method | Pre-or Post Qualification | Prior or Post Review | Plan vs. Actual | Prep & Submission by Ex Agency | No-objection Date | On-line UNDB Gateway Nat Press | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount in US$ | Date Contract Award | Date Contract Advert | Date Contract Signature | Opening of Let of Credit | Arrival of Goods | Inspection Final Acceptance
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | Plan | 4 - 7 wks | 1 - 1.5 wks | 1.5 - 2 wks | 6 to | 12 wks | 1.5 - 3 wks | 1 - 1.5 wks | Plan |  | 1 wk |  | 1.5-3 wks
[5 empty] | add 7-13 wks |  | Actual | [7 empty] | Actual
List of Contracts
Procurement of additional Laboratory equipments and Consumables | ACE/KNUST/GD/001/2022/23 | 1 | 200000 | NCB | Prequalification | Prior | Plan | 2022-12-05 | 2022-12-15 | 2022-12-30 | 2023-01-05 | 2023-02-04 | 2023-02-19 | 2023-03-01 | Plan | 200000 | 2023-03-08 | 2023-03-18 | 2023-04-07 |  | 2023-04-22 | 2023-05-02
[7 empty] | Actual | 14-Feb -23 | [6 empty] | Actual
Procurement of Material/wood for the erecting of Pergola at the open space on the top of the building to serve as sitting area | ACE/KNUST/GD/002/2022/23 | 1 | 100000 | NCB | Prequalification | Prior | Plan | 2022-12-05 | 2022-12-10 | 2023-01-09 | 2023-01-19 | 2023-02-18 | 2023-02-28 | 2023-03-20 | Plan | 100000 | 2023-04-04 | 2023-04-14 | 2023-05-04 |  | 2023-05-19 | 2023-05-29
[7 empty] | Actual | 13-Jan-23 | [6 empty] | Actual
Procurement of Teaching equipments, laptops, E-learning facilities, signages, security gargets etc. | ACE/KNUST/GD/003/2022/23 | 1 | 80000 | NCB | Prequalification | Prior | Plan | 2022-12-05 | 2022-12-10 | 2023-01-09 | 2023-01-19 | 2023-02-18 | 2023-02-28 | 2023-03-20 | Plan | 80000 | 2023-04-04 | 2023-04-14 | 2023-05-04 |  | 2023-05-19 | 2023-05-29
|  |  |  | PQ |  |  | Actual | 24-Feb- 23 |  |  |  | 23-Mar-23 |  |  | Actual
Procurement of Office Equipments, Office Furniture & Fittings, Interior skimming & Décor, etc | ACE/KNUST/GD/004/2022/23 | 1 | 50000 | NCB | Prequalification | Prior | Plan | 2023-12-05 | 2023-12-10 | 2024-01-09 | 2024-01-19 | 2024-02-18 | 2024-02-28 | 2024-03-19 | Plan | 50000 | 2024-04-03 | 2024-04-13 | 2024-05-03 |  | 2024-05-18 | 2024-05-28
|  |  |  | PQ |  |  | Actual | 10-Jan-23 |  |  |  | 23-Mar-23 |  |  | Actual
Procurement of Material and Partitioning of two Engineering Labs, Lecture Theatre, Office Space for receipttion and store et, | ACE/KNUST/GD/005/2022/23 | 1 | 50000 | NCB | Prequalification | Prior | Plan | 2023-12-05 | 2023-12-10 | 2024-01-09 | 2024-01-19 | 2024-02-18 | 2024-02-28 | 2024-03-19 | Plan | 50000 | 2024-04-03 | 2024-04-13 | 2024-05-03 |  | 2024-05-18 | 2024-05-28
|  |  |  | PQ |  |  | Actual | 8-Feb-23 |  |  |  | 23-Mar-23 |  |  | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
Total Cost |  |  | 480000 | [12 empty] | 380000
Fill gray cells only!
Formulas:
No-objection Date = [Prep & Submission by Ex Agency]+10
No-objection Date = [Bid Evaluation]+10
Spec Proc Notice Advert = [No-objection Date]+15
Bidding Period = [Spec Proc Notice Advert]+6
Bid Closing-Opening = [Bidding Period]+30
Bid Evaluation = [Bid Closing-Opening]+15
Date Contract Award = [No-objection Date]+7
Date Contract Advert = [Date Contract Award]+10
Date Contract Signature = [Date Contract Advert]+20
Contract Implementation = [Date Contract Signature]+15
Inspection Final Acceptance = [Contract Implementation]+10

## Works
Country:
Program:
Date:
Applicable Period:
Project ID:
Implementing Agency: | [8 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
|  | Basic Data | [8 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  | Contract Implementation
Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Estimated Amount in US $ | Pre-or Post Qualification | Prior or Post Review | Plan vs. Actual | Prep & Submission by Ex Agency | No-objection Date | On-line UNDB Gateway Nat Press | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount in US$ | Date Contract Award | Date Contract Advert | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost
Norm Duration of Proc Steps | [5 empty] | If Prequalification |  | Plan | 4 - 7 wks | 1 - 1.5 wks | 1.5 - 2 wks | 1.5 - 2 wks | 6 to | 12 wks | 1.5 - 3 wks
[6 empty] | add 7-13 wks |  | Actual | [7 empty] | Plan |  | 1 wk |  | 1.5-3 wks
Actual
List of Contracts
| 1 | 1 | Lumpsum |  |  | Post Qualification | Post Review | Plan |  | N/A | N/A | 3-June-10 | 5-July-10 | 19-July-10 | N/A | Plan | 0 | 3-Aug-10 | 17-Aug-10 | 6-Sept-10
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
Total Cost |  |  |  |  | 0 |  |  | Plan | [8 empty] | 0
Actual
Fill gray cells only!
NB: Submission of BER under NCB implies submission by the Evaluation Committee to Management for Approval, and not to the Bank
Note on O20: wb335051: Submission by Eval. Committee to Mgt not to Bank

## Consultants 2
Country/Organisation:
Programme:
Date:
Applicable Period:
Project ID:
Credit Number:
Implementing Agency:
Request for EOI (where required)
IDA Credit No.: |  | Contract Type |  |  |  | Preparation Request for Proposals |  |  |  | Short List |  |  | Consultant Proposals |  | Proposal Evaluation and Negotiation for Projects after May 2002 Technical (T) & Financial (F) and Negotions (N) | [5 empty] | Draft Contract |  | Contract Finalization |  |  |  |  | Contract Implementation |  |  |  | Remarks
Description* | Selection Method | Lumpsum or Time-Based | Estimated Amount in US$ '000 | Prior/Post Review | Plan vs. Actual | Prep & Submission by Ex Ag | No-objection Date | On-line UNDB Gateway Nat Press | Lead-time before shortlist | Submission Date | No-objection Date | Plan vs. Actual | Invitation Date | Submission/ Opening Date | Submission Evaluation Report (T) | No-objection Evaluation Report (T) | Opening Financial Proposals | Preparation Eval Report (T) (F) | Negotiations (N) | Plan vs. Actual | Submission Date | No-objection Date | Contract Amount in US$ '000 | Contract Award | Date Contract Advert | Contract Signature | Plan vs. Actual | Mobilization Advance Payment | Draft Report | Final Report | Final Cost
Norm Duration of Proc Steps |  |  |  |  | Plan | 3 - 6 wks | 1 - 2 wks | 1 - 1.5 wks | 2 wks |  | 1 - 2 wks | Plan | 4 to | 12 wks | 2 - 3 wks | 0.5 - 2 wks | 2 wks | 1 - 2 wks | 2 wks | Plan | 1 - 2 wks | 1 - 2 wks |  | 1 wk |  | 1 - 3 wks | Plan
Component 1:(Instititional Development)
| QCBS | Lump Sum |  | Prior Review | Plan | 1-April-10 | 15-April-10 | 21-April-10 | 3-May-10 | 10-May-10 | 17-May-10 | Plan | 20-May-10 | 17-June-10 | 1-July-10 | 8-July-2010 | 26-July-2010 | 3-Aug-10 | 10-Aug-10 | Plan | 16-Aug-10 | 23-Aug-10 | 0 | 10-Nov-10 | 30-Aug-10 | 7-Sept-10 | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | 24-Sep-10 | 25-Oct-10 | N/A | N/A | 04-Nov-10 | 11-Nov-10 | 18-Nov-10 | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | N/A | N/A | N/A | N/A | N/A | N/A | 27-Jul-10 | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
0
Consultancy Services for the Supervision of Routine Maintenance of Roads (10 Lots @US$60,000 per Lot)