## Sheet1
Name of Center | KNUST ENGINEERING EDUCATION PROJECT
Institution | Kwame Nkrumah University of Science and Technology |  |  | On Schedule
Country | GHANA
Center Leader | Professor Jerry John Kponyo |  |  | Behind Schedule
Annual Workplan (Month XXX-Month XXX, Year) | JANUARY 2024-DECEMBER 2024
Work Plan Activities | Description | Partner Contribution (if relevant) | 2024 Q1 |  |  | 2024 Q2 |  |  | 2024 Q3 |  |  | 2024 Q4 |  |  | Milestone/Output | If NEW, Provide Justification | Estimated Budget($) | Estimated Revenue ($) | Contribution from Partner ($) | Person Responsible
|  |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Action 1: Centre Governance
Sub-Action 1a: Industrial Advisory Board
Activity 1: Quarterly meetings | Meeting to brief members on current status of project and receive suggestions and opinions to ensure project is relevant to needs of industry | [13 empty] | IAB meeting held every quarter with minutes attached |  | 2000 |  |  | Project Lead, Project Manager
Sub-Action 1b:International Scientific Advisory Board
Activity 1: Quarterly meetings | Meeting members to brief them of progress especially in the research thematic areas and seeking for views to enhance the quality of research | [13 empty] | ISAB meeting held every quarter with minutes attached |  | 2000 |  |  | Project Lead, Project Manager
Action 2: DLI 3:Quantity of Students
Sub-Action 2a: Media Advertisement
Activity 1: Advert of admissions on electronic and print media | Putting the call for admissions on the websites and dailies | [13 empty] | To ensure that all eligible students have access to the information to apply |  | 2000 |  |  | Marketing/Outreach Officer, Project Manager
Sub-Action 2b: Recruitment of students (15 PhDs and 20 MSc's)
Activity 1: Admission of students by departments | Postgraduate students admitted into the various departments | [13 empty] | Postgraduate students admitted into thematic labs |  |  |  |  | Thematic Leads
Activity 2: Students shortlisted for scholarships | Postgraduate students meeting scholarship policy criteria shortlisted | [13 empty] | Scholarship list compiled |  |  |  |  | Thematic Leads, Heads of Departments, Deputy Project Lead, Project Manager
Activity 3: Scholarship interviews held | Panel constituted to conduct interviews | [13 empty] | Scholarship interview held with eligible list compiled |  | 4000 |  |  | Research Thematic Leads, Deans, Heads of Departments
Activity 4: Payment of tuition fees, accommodation and stipends | Postgraduate students tuition fees paid to the college | [13 empty] | Postgraduate students tuition fees paid to the college |  | 549000 |  |  | Project Accountant
Sub-Action 3a: Accreditation
Activity 1: Conducting an International Accreditation | Resubmission of additional information to AQAS in relation to MPhil and PhD Telecommunication Engineering | [13 empty] | Accreditation Certificates for MPhil and PhD in Telecommunication Engineering received from AQAS |  |  |  |  | AQAS, Head of Telecommunication Engineering
Sub-Action 3b: Design of New Courses
Activity 1: Curriculum for new course under the Energy Theme developed subject to recommendation from Gap Assessment | Curriculum for new course under the Energy Theme developed subject to recommendation from Gap Assessment | [13 empty] | New course under the Energy Theme presented to the College Boatd for approval |  | 2000 |  |  | Head of Mechanical Engineering
Activity 2: Curriculum for new course under the Digital Theme developed subject to recommendation from Gap Assessment | Curriculum for new course under the Digital Theme developed subject to recommendation from Gap Assessment | [13 empty] | New programme in PHD, MPhil & MSc in Machine Learning introduced |  | 2000 |  |  | Head of Computer Engineering
Sub-Action 3c: Postgraduate building and Procurement
Activity 1: Creation of research labs | Creation of additional labs under the thematic areas to enhance quality of postgraduate research | [13 empty] | Research labs fully operational |  | 100000 |  |  | Thematic Leads
Activity 2 : Purchase of additional equipment for the thematic Labs | Equipping the thematic labs with equipment to meet new engineering trends | [13 empty] | Additional equipment purchased |  | 100000 |  |  | Thematic Leads
Activity 3: Purchase of a bus | Purchase of a bus to facilitate industry visits and field work | [13 empty] | Bus Purchased |  | 120000 |  |  | Project Accountant, Director of Procurement
Action 4: DLI 5:Relevance of Education
Sub-Action 4a: Internships
Activity 1: 100 Internships for students and faculty members | Internships to bridge the relationship between academia and industry and to make academa more responsive to the needs of industry | [13 empty] | 100 Faculty members and students internships completed with list submitted to AAU for verification |  | 35000 | 100000 |  | Partnership Coordinator, Project Manager
Sub-Action 4b: Regional Conference and Capacity Building
Activity 1: College of Engineering Conference held | Conference for students held for them to present their research findings to stakeholders in industry | [13 empty] | Conference held with support of industry for relevant research areas thereby helping bridge the gap between academia and industry |  | 10000 |  |  | Deputy Project Lead, Postgraduate Coordinators
Activity 2: Staff and Faculty Training | Staff and Faculty members to participate in relevant workshops and conferences in relation to postgraduate engineering education and project management | [13 empty] | Staff and Faculty members travelling to participate in workshops and conferences both in and outside Ghana |  | 45000 |  |  | Project Manager, Project Accountant
Sub-Action 4c: College of Engineering Innovation Fund and Seminar Series
Activity 1: Promoting entrepreneurship, innovations through CoE Innovation Fund | Call for proposals rolled out (third cohort) | [13 empty] | Support granted to successful students |  | 25000 |  |  | Quality Assurance and Innovations Coordinator, Innovation Manager
Activity 2: Commercialisation and Registration of innovations | Innovations under cohort 2 fully commercialised and registered | [13 empty] | Registration of start-ups which are fully operational. Start-ups will be mentored by industry players |  | 15000 |  |  | Quality Assurance and Innovations Coordinator, Innovation Manager
Activity 3: Seminars delivered by industry players | Seminars under the various thematic areas held | [13 empty] | Capacity building on entrepreneurship and innovation held, Academia-Industry relationship enhanced |  | 10000 |  |  | Research Thematic Leads, Innovation Manager
Activity 4: Recruitment of a Training Coordinator for the Innovation Centre | Training Coordinator to take charge of training undertaken by the College of Engineering Innovation Centre | [13 empty] | Training Coordinator recruited |  | 5000 |  |  | Project Lead, Project Manager, Innovation Manager
Action 5: DLI 6: Timeliness and Quality of Fiduciary Management
Sub-Action 5a: Timely Fiduciary Reporting
Activity 1: Financial and Procurement Audit prepared | Audit to ensure that we are adhering to the world class standards of financial management practices | [13 empty] | Audit for the year 2023 completed and uploaded to the KEEP website |  | 10000 | 70000 |  | Project Accountant
Activity 2: IFR for the period ending June 30th and Dec, 31st prepared | KEEP to ensure that IFR is prepared, reviewed and uploaded to website | [13 empty] | IFR will be prepared, reviewed and uploaded to website on 14th Aug for June report and 14th February for the December, |  |  |  |  | Project Accountant
Sub-Action 5b: Web Transaprency of ACE Expenditures
Activity 1: Annual work plan for 2024 will be prepared and approved, budget, IFR and Procurement Audit reports completed | Annual work plan for 2024 will be prepared and approved, budget, IFR and Procurement Audit reports uploaded to website | [13 empty] | Annual work plan for 2024 will be prepared and approved, budget, IFR and Procurement Audit reports uploaded to website |  |  | 70000 |  | Project Accountant
Action 5: Communication
Activity 1: Production of quarterly newsletters | Communication Officer, Content and Production Editors agree on the content for the newsletter | [13 empty] | Newsletter circulated to all stakeholders |  | 3000 |  |  | Communications Officer
Activity 2: Design and print KEEP brochures, pull ups, flyers and souvenirs | Design and print KEEP brochures, pull ups, flyers and souvenirs (calendars, pens, t shrts) | [13 empty] | Visibility of KEEP enhanced |  | 3000 |  |  | Communications Officer
Activity 3: Working on documentaries, jingles, short videos and advertising KEEP on traditional social media | Documentaries, Jingles and short videos in wide circulation on social media platforms | [13 empty] | Enhancing of visibility on social media platforms |  | 2000 |  |  | Communications Officer
Activity 4: Working on KEEP Impact Report | Relaying to stakeholers the impact made by KEEP in relation to the Disbursement Link Indicators (DLI's) | [13 empty] | Distributing the Impact Report to stakeholders |  | 2000 |  |  | Communications Officer
Activity 5: Interview of Thematic Leads and Faculty members on cross-cutting research taking place | Interview of Thematic Leads and Faculty members on cross-cutting research taking place | [13 empty] | Impact reports printed in hard prints and also located on social media platforms |  | 2500 |  |  | Communications Officer
Activity 6: Recruitment of Project Graphic Designer and Assistant Communication Officer | Project Designer and Assistant Communications Officer to assist Communications Officer in the design and timely dissemination of information | [13 empty] | Project Graphic Designer and Assistant Communications Officer recruited |  | 5000 |  |  | Project Lead, Project Manager, Communications Officer
Action 6: Alumni Relations
Activity 1 : Registration of Alumni | Capturing database of alumni who have completed the College of Engineering | [13 empty] | Registration of Alumni ongoing |  |  |  |  | Alumni Relations Officer
Activity 2: Alumni Chapter Meetings | Holding meetings with Alumni in the various regions and diasporaon a quarterly basis | [13 empty] | Chapter meetings held |  | 20000 |  |  | Alumni Relations Officer
[17 empty] | 1071500 | 240000
Note on U6: Schenineda: If the addition of an activity or component requires further clarification, state it. Expecially since COVID may alter center activities and focus
Note on B17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: We are now admitting them into research labs. Please revise that.
Note on A41: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Innovation Manager to discuss this
Note on A58: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Confirm the frequency of the meetings and whether it includes Alumni in the diaspora